## ProductBacklog
PRODUCT BACKLOG
|  |  | Batch 2018_2019 | COSMO APP
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
|  | Admin | Login using a Static 'USER ID' and 'PASSWORD" | I Can control Admin panel
|  | Admin | Check all the user Details | I Can know About All the Users
|  | Admin | Manages Appointment | I Can handle all the very Eaisly
|  | admid | give a perticular time sot to the costomer | I can give the time slot to the customers
|  | Admin | manages available therepy | I Can provides better therepy Service to customer
|  | Admin | Take the Query | I Can Solve the customers Problem Or Query
|  | Admin | Check Payment History | I Can Check that I have receive fee of therepy or not
|  | Admin | Check History Of All Query | There is no one customer which any problem according to his requirement
|  | User | Check his /her details | I Can Check my profile
|  | User | Book For an Appointment | I Can book an Appointment for therepy
|  | User | know about available therepy | I Can know the over all cost of therepy and about therepy
|  | User | Consult With specialist After payment | I Can about my treatment
|  | User | give feedback | I can suggest for beter service

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - IOT BASED DUSTBIN
SB1/US1 | cosmo application | SB1/D1/T1 | Design the GUI | SAURAV KUMAR JHA | In progress | 2018-09-12
|  | SB1/D1/T2 | Coding | SAURAV KUMAR JHA | In progress | 2018-09-12
|  | SB1/D1/T3 | Connect with Database | SAURAV KUMAR JHA | In progress | 2018-09-12
SB1/US2 | Receive the notification of the appoinment | SB1/D2/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-12
|  | SB1/D2/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-12
|  | SB1/D2/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-12
SB1/US3 | check available therpy | SB1/D3/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D3/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D3/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US4 | check user details | SB1/D4/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D4/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D4/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US5 | provide solution of problems | SB1/D5/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D5/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D5/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US6 | payment history | SB1/D6/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D6/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D6/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US7 | history of all feedback | SB1/D7/T1 | Design the GUI | SAURAV KUMAR JHA | Not Started | 2018-09-18
|  | SB1/D7/T2 | Coding | SAURAV KUMAR JHA | Not Started | 2018-09-18
|  | SB1/D7/T3 | Connect with Database | SAURAV KUMAR JHA | Not Started | 2018-09-18
SB1/US8 | Request of appointment | SB1/D8/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D8/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D8/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US9 | payment merchant | SB1/D9/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D9/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D9/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18
SB1/US10 | feedback | SB1/D10/T1 | Design the GUI | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D10/T2 | Coding | RAHUL OJHA | Not Started | 2018-09-18
|  | SB1/D10/T3 | Connect with Database | RAHUL OJHA | Not Started | 2018-09-18

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 90 | Tasks
2018-09-12 | 120 | 90
2018-09-11 | 80 | 50
2018-09-14 | 56 | 27
2018-09-16 | 15 | 12
2018-09-18 | 5 | 2
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - IOT BASED DUSTBIN
SB2/US1 | Set the system | SB2/D1/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D1/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D1/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US2 | Fix the GSM module | SB2/D2/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D2/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D2/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US3 | Fix the GPS | SB2/D3/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D3/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D3/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US4 | Fix the google api | SB2/D4/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D4/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D4/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US5 | Fix the weight sensor | SB2/D5/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D5/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D5/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US6 | Fix the height sensor | SB2/D6/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D6/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-02
|  | SB2/D6/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-02
SB2/US7 | Update the system | SB2/D7/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D7/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D7/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07
SB2/US8 | Fix the sms API | SB2/D8/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D8/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D8/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07
SB2/US9 | Details of drivers | SB2/D9/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D9/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D9/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07
SB2/US10 | Details of sweepers | SB2/D10/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D10/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D10/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07
SB2/US11 | Details of dustbin | SB2/D11/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D11/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D11/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07
SB2/US12 | Details of truck | SB2/D12/T1 | Design the GUI | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D12/T2 | Coding | raghuveer sing bhati | Not Started | 2018-10-07
|  | SB2/D12/T3 | Connect with Database | raghuveer sing bhati | Not Started | 2018-10-07

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days